## Team Backlog
Task Name | Assignee | Progress | Expected Time | Actual Time
LCD Desgin | Ahmed Atef | DONE | 17/4/2023 | 17/4/2023
LM35 Design | Ahmed Hesham | DONE | 17/4/2023 | 17/4/2023
Keypad Design | Ahmed Hesham | DONE | 17/4/2023 | 17/4/2023
ADC Design | Momen Hassan | DONE | 17/4/2023 | 17/4/2023
Buzzer Design | Momen Hassan | DONE | 17/4/2023 | 17/4/2023
LCD Driver | Ahmed Atef | DONE | 18/4/2023 | 18/4/2023
LM35 Driver | Ahmed Hesham | DONE | 18/4/2023 | 18/4/2023
Keypad Driver | Ahmed Hesham | DONE | 18/4/2023 | 18/4/2023
ADC Driver | Ahmed Hesham | DONE | 18/4/2023 | 18/4/2023
Buzzer Driver | Ahmed Hesham | DONE | 18/4/2023 | 18/4/2023
Application Design | Ahmed Hesham | DONE | 19/4/2023 | 19/4/2023
Application Development | Team | DONE | 19/4/2023 | 19/4/2023
Application Testing | Team | DONE | 19/4/2023 | 19/4/2023

## Test Cases Sheet
Test Case ID | Description / steps | Expected Results | Actual Results | Progress
1 | Testing Timer delay + timer interrupt | led 0 toggle after 1 sec using TIMER_delay then led 1 toggle every 2 sec using ovf interrupt | Same as expected | PASS
2 | Testing LM35 | when temp > 25 led 1 on led 2 off, when temp <= 25 led 1 off led 2 on. | Same as expected | PASS
3 | Testing Keypad | representing keypad's buttons value binary on 4 leds | Same as expected | PASS
4 | Testing Application; press set button, wait 2 seconds, press reset button, wait two seconds press adjust, wait 10 secs, press increment button. | after pressing set button, buzzer will be on + bell shape at the beginning, after pressing reset button and waiting 10 seconds it will timeout from setting state and go to idle state of showing current temp + bell shape if it's higher than desired temp, after pressing increment button will print this operation is not allowed. | Same as expected | PASS
5 | Testing Application; During setting state press increment till it exceeds 35 | with every press a bell shape will be drawn in the second line representing number of degrees after reaching 35 increment button will not have any effect | Same as expected | PASS
6 | Testing Application; During setting state press decrement till it exceeds 18 | with every press a bell shape will be deleted from the second line representing number of degrees after reaching 18 decrement button will not have any effect | Same as expected | PASS
7 | Testing Application; During Idle state increase and decrease exposed temperature to temperature sensor | LCD will print current temperature as the temperature measured from temperature sensor | It sometimes prints the same temperature and sometimes prints a higher or lower temperature by 1 degree | NEUTRAL